## Sheet2
start_date | end_date | event | height
Jan 5, 2015 | Jan 29, 2015 | Team trip to Patna and Mumbai
Jan 10, 2015 | Jan 10, 2015 | Formal provider interactions started in Patna
Feb 1, 2015 |  | All hands meeting where Patna baseline design for SP surveillance and trial presented
Feb 25, 2015 |  | ISERDD finishes Patna baseline fieldwork (started Nov 5, 2014)
Mar 16, 2015 | Mar 17, 2015 | QuTUB Baltimore meeting
Mar 22, 2015 | Mar 31, 2015 | SP training in Mumbai
Apr 1, 2015 |  | All hands meeting
Apr 25, 2015 |  | CME in Patna & WHP-QuTUB results dissemination
Apr 27, 2015 | May 1, 2015 | Meetings with PATH to set up AYUSH trial procedures
May 20, 2015 |  | All hands meeting
Jun 11, 2015 | Jun 12, 2015 | Two day MLE meeting
Jun 22, 2015 | Jul 20, 2015 | Ada/Ben trip to Mumbai to set up provider-specific interactions at hubs
Aug 10, 2015 |  | Delhi pilot paper published online
Sep 7, 2015 |  | IRB renewed and protocol additions accepted by McGill REB
Sep 25, 2015 | Sep 26, 2015 | QuTUB DC meeting
Apr 5, 2015 | Aug 11, 2015 | Mumbai SP Fieldwork (baseline) | 1
Jan 1, 2015 | Feb 25, 2015 | Patna SP Fieldwork (baseline) | 1